## 1.2 - Financial responsible
| Column A | Column B | Column C | Column D
Row 1 | Annex 1 - Breakdown of tasks & costs
Row 2 | 1.2 - Financial Breakdown
Row 3 | 1 | Speakers | Financial reponsibility | Comments
Row 4 | 1.1 | Travel, Accomodation and fees for speakers
Row 5 | 1.1.1 | Internationally renown Keynote speakers/lecturers | CO-HOST | A budget should be set beforehand for all speakers. A significant portion of this budget should be destined to keynote speakers
Row 6 | 1.1.2 | International speakers | CO-HOST
Row 7 | 1.1.3 | National speakers | CO-HOST
Row 8 | 2 | Main Congress venue
Row 9 | 2.1 | Venues rental | CO-HOST
Row 10 | 2.2 | Venue Services | CO-HOST
Row 11 | 2.3 | Signage and postages
Row 12 | 2.3.1 | Signage and postages for venue organization | CO-HOST
Row 13 | 2.3.2 | Decor | CO-HOST
Row 14 | 2.3.3 | Congress branding | EBN and CO-HOST
Row 15 | 2.4 | Catering
Row 16 | 2.4.1 | Coffee Breaks | CO-HOST
Row 17 | 2.4.2 | Lunch(es) | CO-HOST
Row 18 | 2.4.3 | Cocktail(s) | CO-HOST
Row 19 | 2.4.4 | Additional (i.e) Breakfast, drinks in networking, tbd | CO-HOST
Row 20 | 2.5 | Logistics and Equipment
Row 21 | 2.5.1 | Furniture | CO-HOST
Row 22 | 2.5.2 | Lights | CO-HOST
Row 23 | 2.5.3 | Sound | CO-HOST
Row 24 | 2.5.4 | AV/IT | CO-HOST
Row 25 | 2.5.5 | Internet | CO-HOST
Row 26 | 2.5.6 | Exhibitor area and equipment (Sponsors)
Row 27 | 2.5.6.1 | Exhibitor area and equipment (EBN Projects) | EBN | If appliable
Row 28 | 2.5.6.2 | Stationery | CO-HOST | If appliable
Row 29 | 2.5.6.3 | Exhibitor area and equipment (Local and National exhibitors) | CO-HOST | If appliable
Row 30 | 2.6 | Translation to english | CO-HOST | If appliable
Row 31 | 2.7 | Security | CO-HOST
Row 32 | 2.8 | Cleaning | CO-HOST
Row 33 | 2.9 | Hosting services | CO-HOST
Row 34 | 2.1 | Support Labour | CO-HOST
Row 35 | 2.11 | Additional | CO-HOST | If needed
Row 36 | 3 | Organize Dinner and external activities
Row 37 | 3.1 | Dinner Venue | CO-HOST
Row 38 | 3.2 | Hire catering | CO-HOST
Row 39 | 3.3 | Extra - entertainment - activities | CO-HOST
Row 40 | 3.4 | AV/IT | CO-HOST | If appliable
Row 41 | 3.5 | Organisation of site visits of cultural or thematic interest to the event/region | CO-HOST
Row 42 | 3.6 | transportation and entertainment for visits | CO-HOST
Row 43 | 4 | Transportation + Stays
Row 44 | 4.1 | Organise transfers | CO-HOST | If appliable
Row 45 | 4.2 | Agreements with hotel(s) | CO-HOST
Row 46 | 5 | Communication and Visuals
Row 47 | 5.1 | Local Images, footage, and logos | CO-HOST
Row 48 | 5.2 | Website | EBN
Row 49 | 5.3 | Visual and communication identity - assets | EBN
Row 50 | 5.4 | Video promotion | CO-HOST | if applicable
Row 51 | 5.4.1 | Pre-programme promotion focused on region and host | EBN | If appliable
Row 52 | 5.4.2 | Video of the event (post event) | CO-HOST | If appliable
Row 53 | 5.5 | EBN Congress Banners | EBN
Row 54 | 5.6 | Physical promotion materials | CO-HOST
Row 55 |  | Social media campaign | EBN
Row 56 | 6 | Online elements
Row 57 | 6.1 | Networking app | CO-HOST
Row 58 | 7 | Support materials
Row 59 | 7.1 | Goodie bags and its content | CO-HOST
Row 60 | 7.2 | Badges + Lanyards | EBN
Row 61 | 7.3 | Hire local support (i.e. Photo + Video) | CO-HOST

## 1.3 - Accountability - RACI
| Column A | Column B | Column C | Column D | Column E | Column F | Column G
Row 1 | Annex 1 - Breakdown of tasks & costs | [6 empty] | Responsible: a manager or team member who is directly responsible for successfully completing a project task. Accountable: the person with final authority over the successful completion of the specific task or deliverable. Consulted: someone with unique insights the team will consult. Informed: a client or executive who isn’t directly involved, but you should keep up to speed.
Row 2 | 1.3 - Accountability - RACI
Row 3 | 1 | Frame: Content | R | A | C | I | Comment | https://monday.com/blog/project-management/raci-model/
Row 4 |  |  | Responsible | Acountable | Consulted | Informed
Row 5 | 1.2 | Preparation
Row 6 | 1.1.1 | Set up dedicated teams and regular collaboration schedule | EBN event manager | Host event manager
Row 7 | 1.1.2 | pre-determine tasks and division of labour | EBN event manager | Host event manager | Both C-suite | Both comms
Row 8 | 1.1.3 | pre-Determine dates | Host C-suite | EBN C-suite | Both event manager | Both comms
Row 9 | 1.1.4 | Determine preliminary budget and its division | Host financial | EBN financial | Both C-suite | Both event manager
Row 10 | 1.1.5 | Set goals | EBN event manager | Host event manager | Both C-suite | Both comms
Row 11 | 1.1.6 | Set Target Audiences | EBN event manager | Host event manager | Both C-suite | Both comms
Row 12 | 1.1.7 | Decide prices and offers | Host financial | EBN financial | Both C-suite | Both event manager
Row 13 | 1.1.8 | Define overall themes | Host C-suite | EBN C-suite | Both event manager | Both comms
Row 14 | 1.1.9 | Define potential partners | Host C-suite | EBN C-suite | Both event manager | Both comms
Row 15 | 1.1.10 | Pre-define Potential Sponsors | Host C-suite | EBN C-suite | Both event manager | Both comms
Row 16 | 1.1.11 | Create shared Budget document | EBN event manager | Host event manager | Both financial | Both C-suite
Row 17 | 1.2 | Programme
Row 18 | 1.2.1 | Define format | EBN event manager | Host event manager | Both C-suite | EBN comms
Row 19 | 1.2.2 | Create Programme Structure | EBN event manager | Host event manager | Both C-suite | EBN comms
Row 20 | 1.2.3 | Decide Programme Themes | EBN event manager | Host event manager | Both C-suite | EBN comms
Row 21 | 1.2.4 | Define Specific panel themes | EBN event manager | Host event manager | Both C-suite | EBN comms
Row 22 | 1.2.5 | Prepare agenda | EBN event manager | Host event manager | Both C-suite | EBN comms
Row 23 | 1.2.5.1 | Assign RACI per Panel | Both C-suite | Both event manager | Host staff lead | EBN staff lead
Row 24 | 1.2.5.2 | determine Speaker profiles | Both event manager | Both staff leads | Both C-suite
Row 25 | 1.2.5.3 | Manage speakers | Both staff leads | Both event manager
Row 26 | 1.2.5.4 | Set up meetings (pre-with moderator, pre with all, on site Meeting | Both staff leads | Both event manager
Row 27 | 1.2.5.5 | Collect information | Both staff leads | Both event manager |  | Both comms
Row 28 | 1.2.5.6 | make sure registration is all correct | Both staff leads | EBN event manager
Row 29 | 1.2.6 | Comms
Row 30 | 1.2.6.1 | Set the tag-line | EBN event manager | Host event manager | Both comms
Row 31 | 1.2.6.2 | Write overall Blurb | EBN event manager | Host event manager | Both comms
Row 32 | 1.2.6.3 | Write Blurb per session | Both staff leads | Both event manager | Both comms
Row 33 | 1.2.6.4 | Write the Final full Session description | EBN event manager | Host event manager | Both comms | Both staff leads
Row 34 | 1.3 | Speakers
Row 35 | 1.3.1 | Establish list of desired speakers | Both event manager | Both staff leads | Both C-suite
Row 36 | 1.3.2 | Create invitation documents | EBN event manager | Host event manager | Both C-suite | Both comms
Row 37 | 1.3.3 | Send invitations | Both staff leads | Both event manager | Both C-suite | Both comms
Row 38 | 1.3.4 | Confirm all speakers | Both staff leads | Both event manager | Both C-suite | Both comms
Row 39 | 1.3.5 | Management of speaker budget | EBN event manager | Host event manager | Both C-suite | Both comms
Row 40 | 1.3.6 | Prepare Speaker Logistics - Physical or digital Briefing | Host event manager | Host event manager | Both staff leads | Both C-suite
Row 41 | 1.3.7 | Accomodation speakers | Host event manager | Host staff lead | EBN event manager | EBN staff lead | If they need support identifying best providers for them
Row 42 | 1.3.8 | Transportation speaker | Host event manager | Host staff lead | EBN event manager | EBN staff lead | If they need support identifying best providers for them
Row 43 | 1.3.9 | Coordinate collect and display of presentation material | Host staff lead | EBN staff lead | EBN event manager | Host event manager
Row 44 | 1.3.10 | Comms
Row 45 | 1.3.10.1 | Get Speakers' Bio and photos + consent to promote | Both staff leads | EBN event manager | EBN comms | Host comms
Row 46 | 1.4 | Sponsors
Row 47 | 1.4.1 | Set goals for sponsors | Both C-suite | Both event manager | Both staff leads | Both comms
Row 48 | 1.4.2 | Contact potential Sponsors | To be filled in | Both C-suite | Both event manager | Both staff leads
Row 49 | 1.4.3 | Confirm Sponsors | Both C-suite | Both event manager | Both staff leads | Both comms
Row 50 | 1.4.4 | Start promoting their role in Congress | EBN comms | Host comms | Both event manager | Both C-suite
Row 51 | 1.4.5 | Acquire any copy needed from sponsors | EBN comms | Host comms | Both event manager | Both C-suite
Row 52 | 1.4.6 | Comms
Row 53 | 1.4.6.1 | Copy + materials to reflect in comms | EBN comms | Host comms | Both event manager | Both C-suite
Row 54 | 1.4.6.2 | Acquire all logos - sponsors, partners, etc.. | EBN comms | Host comms | Both event manager | Both C-suite
Row 55 | 2 | Frame: Logistics
Row 56 | 2.1 | Venue Main event
Row 57 | 2.1.1 | Research possible venues - digital and non-digital | Host event manager | Host C-suite | EBN event manager | Both comms
Row 58 | 2.1.2 | Visit/review venue(s) | Host event manager | Host C-suite | EBN event manager | Both comms
Row 59 | 2.1.3 | Book venue(s) | Host event manager | Host C-suite | EBN event manager | Both comms
Row 60 | 2.1.4 | Set a venue(s) / event flow | Host event manager | Host C-suite | EBN event manager | Both comms
Row 61 | 2.1.5 | Set venue(s) look and feel | Host event manager | Host C-suite | EBN event manager | Both comms
Row 62 | 2.1.6 | Define services | Host event manager | Host C-suite | EBN event manager | Both comms
Row 63 | 2.1.7 | Define signage and postages | Host event manager | Host C-suite | EBN event manager | Both comms
Row 64 | 2.1.8 | Safety protocol | Host event manager | Host C-suite | EBN event manager | Both comms
Row 65 | 2.1.9 | Catering in venue
Row 66 | 2.1.9.1 | Coffee Breaks 2 Days | Host event manager | Host C-suite | EBN event manager | Both comms
Row 67 | 2.1.9.2 | Lunch | Host event manager | Host C-suite | EBN event manager | Both comms
Row 68 | 2.1.9.3 | Cocktail | Host event manager | Host C-suite | EBN event manager | Both comms
Row 69 | 2.1.9.4 | Additional (i.e) Breakfast, drinks in networking, tbd | Host event manager | Host C-suite | EBN event manager | Both comms
Row 70 | 2.1.10 | Logistics and Equipment
Row 71 | 2.1.10.1 | Furniture | Host event manager | EBN event manager | Host C-suite | Both comms
Row 72 | 2.1.10.2 | Lights | Host event manager | EBN event manager | Both staff leads | Both comms
Row 73 | 2.1.10.3 | Sound | Host event manager | EBN event manager | Both staff leads | Both comms
Row 74 | 2.1.10.4 | AV/IT | Host event manager | EBN event manager | Both staff leads | Both comms
Row 75 | 2.1.10.5 | Internet | Host event manager | EBN event manager | Both staff leads | Both comms
Row 76 | 2.1.10.6 | Exhibitor area and equipment (Sponsors) | Host event manager | EBN event manager | Both staff leads | Both comms
Row 77 | 2.1.10.7 | Exhibitor area and equipment (EBN Projects) | Host event manager | EBN event manager | Both staff leads | Both comms
Row 78 | 2.1.10.8 | Stationery | Host event manager | EBN event manager | Both staff leads | Both comms
Row 79 | 2.1.10.9 | Exhibitor area and equipment (Local and National exhibitors) | Host event manager | Host C-suite | EBN event manager | Both comms
Row 80 | 2.1.10.10 | Translation to english if appliable | Host event manager | Host C-suite | EBN event manager | Both comms
Row 81 | 2.1.10.11 | Security | Host event manager | Host C-suite | EBN event manager | Both comms
Row 82 | 2.1.10.12 | Cleaning | Host event manager | Host C-suite | EBN event manager | Both comms
Row 83 | 2.1.10.13 | Host services | Host event manager | Host C-suite | EBN event manager | Both comms
Row 84 | 2.1.10.14 | Support Labour | Host event manager | Host C-suite | EBN event manager | Both comms
Row 85 | 2.1.30 | Additional | Host event manager | Host C-suite | EBN event manager | Both comms
Row 86 | 2.1.11 | Comms
Row 87 | 2.1.11.1 | Guide | Host comms | EBN comms | Both event manager | Both comms
Row 88 | 2.1.11.2 | Signage and postage in venues + Decor and Branding | Host comms | EBN comms | Both event manager | Both comms
Row 89 | 2.1.11.3 | Images and logos (if appliable) | Host comms | EBN comms | Both event manager | Both comms
Row 90 | 2.2 | Organize Dinner and external activities
Row 91 | 2.2.1 | Dinner Venue | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 92 | 2.2.2 | Identify and hire caterers | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 93 | 2.2.3 | Headcount estimate | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 94 | 2.2.4 | Agree menus for meals | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 95 | 2.2.5 | Arrange Extra activities | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 96 | 2.2.6 | Final headcount check | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 97 | 2.3 | Transportation + Stays
Row 98 | 2.3.1 | Identify transportation + Accomodation needs | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 99 | 2.3.2 | Organise transfers | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 100 | 2.3.3 | Identify Partner hotels | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 101 | 2.3.4 | Identify transportation partners | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 102 | 2.3.5 | Arrange agreements | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 103 | 2.3.6 | Identify Partners (Communication + Traveling + Tourism etc… | Host event manager | Host C-suite | EBN event manager | EBN C-suite
| 2.4 | Visits
Row 104 | 2.4.1 | Organisation of site visits of cultural or thematic interest to the event | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 105 | 2.4.2 | Determining the programme of these visits | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 106 | 2.4.3 | Inviting contributions to these visits | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 107 | 2.4.4 | organising transportation and entertainment for visits | Host event manager | Host C-suite | EBN event manager | EBN C-suite
Row 108 | 3 | Communication and Visuals
Row 109 | 3.1 | Preparation
Row 110 | 3.1.1 | Local Images, footage, and logos (if appliable) | Host comms | EBN comms | EBN event manager | Host event manager
Row 111 | 3.1.2 | Communication planning | EBN comms | Host comms | EBN event manager | Host event manager
Row 112 | 3.1.3 | Identify Comms partners | EBN comms | Host comms | EBN event manager | Host event manager
Row 113 | 3.1.4 | Highlight partners on Website | EBN comms | Host comms | EBN event manager | Host event manager
Row 114 | 3.1.5 | Social media kit | EBN comms | Host comms | EBN event manager | Host event manager
Row 115 | 3.1.6 | Visual Assets | EBN comms | Host comms | EBN event manager | Host event manager
Row 116 | 3.1.7 | Videos promotion | Host comms | EBN comms | EBN event manager | Host event manager
Row 117 | 3.1.8 | Banners for promotion | EBN comms | Host comms | EBN event manager | Host event manager
Row 118 | 3.1.9 | Phsysical promotion materials | Host comms | EBN comms | EBN event manager | Host event manager
Row 119 | 3.1.10 | Local Press | Host comms | EBN comms | EBN event manager | Host event manager
Row 120 | 3.1.11 | Press coordination | Host comms | EBN comms | EBN event manager | Host event manager
Row 121 | 3.1.12 | Logistics Guide | Host comms | EBN comms | EBN event manager | Host event manager
Row 122 | 3.2 | Online elements
Row 123 | 3.2.1 | Identify and contract | EBN event manager | Host event manager | Both comms | EBN financial
Row 124 | 3.3 | Communication
Row 125 | 3.3.1 | Visual Identity | EBN comms | Host comms | EBN event manager | Host event manager
Row 126 | 3.3.2 | Visuals Look and feel | EBN comms | Host comms | EBN event manager | Host event manager
Row 127 | 3.3.3 | Fix comms tools | EBN comms | Host comms | EBN event manager | Host event manager
Row 128 | 3.3.4 | Physical and Digital Onboarding Guide | Host comms | EBN comms | EBN event manager | Host event manager
Row 129 | 3.3.5 | Stock videos/Images for promotional material | Host comms | EBN comms | EBN event manager | Host event manager
Row 130 | 3.4 | Promotion
Row 131 | 3.4.3 | Save the date - visual and calendar options | EBN comms | Host comms | EBN event manager | Host event manager
Row 132 | 3.4.4 | Design Website | EBN comms | Host comms | EBN event manager | Host event manager
Row 133 | 3.4.5 | Programme on Website | EBN comms | Host comms | EBN event manager | Host event manager
Row 134 | 3.4.6 | Accomodation on Website | EBN comms | Host comms | EBN event manager | Host event manager
Row 135 | 3.4.7 | Speaker Bio on Website | EBN comms | Host comms | EBN event manager | Host event manager
Row 136 | 3.4.8 | Ticketing on Website | EBN comms | Host comms | EBN event manager | Host event manager
Row 137 | 3.4.9 | General Invitation texts | EBN comms | Host comms | EBN event manager | Host event manager
Row 138 | 3.4.10 | First invitation email | EBN comms | Host comms | EBN event manager | Host event manager
Row 139 | 3.4.11 | Second Invitation email | EBN comms | Host comms | EBN event manager | Host event manager
Row 140 | 3.4.12 | Third invitation email | EBN comms | Host comms | EBN event manager | Host event manager
Row 141 | 3.4.13 | Fourth Invitation email | EBN comms | Host comms | EBN event manager | Host event manager
Row 142 | 3.4.14 | Thank you email (general) + Feedback link | EBN comms | Host comms | EBN event manager | Host event manager
Row 143 | 3.4.15 | Thank you email (specific) | EBN comms | Host comms | EBN event manager | Host event manager
Row 144 | 3.4.16 | Sharing post event materials | EBN comms | Host comms | EBN event manager | Host event manager
Row 145 | 3.4.17 | Social media posts and campaign | EBN comms | Host comms | EBN event manager | Host event manager
Row 146 | 3.5 | Support materials
Row 147 | 3.5.1 | Identify materials required | Host event manager | Host comms | EBN event manager | EBN comms
Row 148 | 3.5.2 | Goodie bags | Host event manager | Host comms | EBN event manager | EBN comms
Row 149 | 3.5.3 | Lanyards | EBN comms | Host comms | EBN event manager | Host event manager
Row 150 | 3.5.4 | Hire local support (i.e. Photo + Video) | Host event manager | Host comms | EBN event manager | EBN comms
Row 151 | 4 | Final check
Row 152 | 4.1 | Set up equipment | Both event manager | Both staff leads | Both C-suite | To be filled in
Row 153 | 4.2 | Set up support materials | Both event manager | Both staff leads | Both C-suite | To be filled in
Row 154 | 4.3 | Check rooms and seating | Both event manager | Both staff leads | Both C-suite | To be filled in
Row 155 | 4.4 | Check catering | Both event manager | Both staff leads | Both C-suite | To be filled in
Row 156 | 4.5 | Check equipment | Both event manager | Both staff leads | Both C-suite | To be filled in
Row 157 | 4.6 | Check materials | Both event manager | Both staff leads | Both C-suite | To be filled in
Row 158 | 4.7 | Check decor | Both event manager | Both staff leads | Both C-suite | To be filled in
Row 159 | 4.8 | The event | Both event manager | Both staff leads | Both C-suite | To be filled in
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Responsible: a manager or team member who is directly responsible for successfully completing a project task.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Accountable: the person with final authority over the successful completion of the specific task or deliverable.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consulted: someone with unique insights the team will consult.
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Informed: a client or executive who isn’t directly involved, but you should keep up to speed.